## Project Information
I. Requirements
Cửa hàng bán đồ ăn nhanh LotteBee là một chuỗi cửa hàng chuyên bán đồ ăn thức uống nhanh nhiều năm nay và đã có một lượng khách hàng nhất định. Để mở rộng hoạt động kinh doanh của mình, công ty mong muốn xây dựng một hệ thống thương mại điện tử nhằm mở rộng phạm vi kinh doanh trên mạng Internet. Hệ thống mới phải đảm bảo cho khách hàng viếng thăm Website dễ dành lựa chọn các sản phẩm, các chính sách của công ty cũng như mua hàng. Việc thanh toán có thể được thực hiện qua mạng hoặc thanh toán trực tiếp. Khách hàng có thể nhận hàng tại cửa hàng hoặc công ty sẽ có dịch vụ chuyển hàng có phí cho khách hàng.Ngoài ra, hệ thống cũng cần có phân hệ để đảm bảo cho công ty quản lý các hoạt động kinh doanh như số lượng hàng có trong kho, quản lý đơn đặt hàng, tình trạng giao hàng v.v…

## Team
TEAM DEVELOPMENT STRUCTURE
No. | Name | Account | Roles | DateStart | Date End
1 | Nguyễn Thanh Tiến | TonyNguyen | Product Owner | 2023-07-02
2 | Nguyễn Nhật Hào | DavidNguyen | ScrumMaster | 2023-07-03
3 | Đào Gia Huy | CrisDao | Dev | 2023-07-04
4 | Lê Hoàng Ngọc | HarryLe | Dev | 2023-07-05

## Product backlog
E-COMMERCE PROJECT - PRODUCT BACKLOG
Story ID | Story Name | Points
Actor : là những bạn trẻ , gia đình truyền thống
1 | View HomePage | 3
2 | View Product list | 3
3 | View Product details | 3
4 | Manage Shopping Cart (Add, Increase, Decrease, Remove) | 3
5 | FeedBack Product | 2
6 | View Product Compare | 2
7 | Chat with Sale | 3
Actor: là thành viên tôi muốn
8 | Login | 2
9 | Make Orders | 3
10 | Order Management (View, Cancel request) | 3
11 | View Shipping Progress | 2
12 | Online Payment | 3
13 | Logout | 1
Actor: là nhân viên xử lý đơn hàng tui muốn
14 | View New Order | 2
15 | Order Management (View, Update) | 3
16 | Shipping Management | 3
Actor : là nhân viên quản lý tui muốn
17 | Product Management | 3
18 | Store Management | 3
19 | Inventory Management | 3
20 | Price Management | 3
21 | Promotion Management | 3
Actor : là nhân viên quản trị trang web
22 | User Management | 4
23 | Product information view | 2
24 | View information store | 2
25 | Inventory information view | 2
26 | Price information view | 2
27 | Promotion information view | 2
28 | View FeedBack Product | 5

## Sprint backlog
E-COMMERCE PROJECT - SPRINT BACKLOG
Story ID | Story Name | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
14
Sprint 1
1 | View HomePage | 3
2 | View Product list | 3
3 | View Product details | 3
4 | View Product Compare | 2
5 | Manage Shopping Cart (Add, Increase, Decrease, Remove) | 3
6 | Chat with Sale | 3
7